## Tasks duration
Initial estimation | WP7 | Sustainability | [47 empty] | ESRF | ILL | XFEL.EU | ESS | ELI | CERIC -ERIC | EGI.eu | Total
| Year | 2018 | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| Month | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Set | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Set | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Set | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Set | Oct | Nov | 3 | 3 | 3 | 3 | 12 | 32 | 0 | 56
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
| Task 7.1 | 18: D 7.1 | 0 | 1 | 1 | 1 | 2 | 7 | 0 | 12
| Task 7.2 | 36: D 7.2 | 1 | 1 | 1 | 1 | 2 | 5 | 0 | 11
| Task 7.3 | 42: D 7.3 | 1 | 0 | 0 | 0 | 4 | 10 | 0 | 15
| Task 7.4 | 48: D 7.4 | 1 | 1 | 1 | 1 | 4 | 10 | 0 | 18
Assessment 09/2020 | [49 empty] | ESRF | ILL | XFEL.EU | ESS | ELI | CERIC -ERIC | EGI.eu | Total
[50 empty] | 3 | 3 | 3 | 3 | 9 | 32 | 0 | 53
[50 empty] | 0 | 1 | 1 | 1 | 2 | 5 | 0 | 10
[50 empty] | 1 | 1 | 1 | 1 | 1 | 4 | 0 | 9
[50 empty] | 1 | 0 | 0 | 0 | 3 | 10 | 1 | 15
[50 empty] | 1 | 1 | 1 | 1 | 3 | 10 | 1 | 18

## Work breakdown
Task | Title | predecessor | start date | end date | Proposed milestone | Comments
Task 7.1 | Stakeholders for the Photon and Neutron community EOSC | - | 2018-12-01 | 2022-11-30
7.1.1 | Overview of the literature | - | 2018-12-01 | 2019-05-28
7.1.2 | Definition of categories of stakeholders | 7.1.1 | 2019-05-28 | 2019-06-30
7.1.3 | Definition of a first set of stakeholders | 7.1.2 | 2019-07-01 | 2019-09-30
7.1.4 | Revision of the list of stakeholders after partners' feedback | 7.1.3 | 2019-10-01 | 2019-12-01
7.1.5 | Definition of potential questions to stakeholders | 7.1.3 | 2019-12-01 | 2020-01-30
7.1.6 | First draft of Deliverable 7.1 | 7.1.4 | 2020-02-01 | 2020-03-30
7.1.7 | Revision of Deliverable 7.1 | 7.1.6 | 2020-04-01 | 2020-05-30
7.1.8 | Consultation with stakeholders | - | 2019-06-30 | 2022-11-30
7.1.9 | Collection of feedback and report | - | 2019-06-30 | 2022-11-30
Task 7.2 | Metrics and cost for the Photon and Neutron community EOSC |  | 2019-08-01 | 2021-11-30
7.2.1 | Define objective, scope and methodology | - | 2019-08-01 | 2020-04-30
7.2.2 | Collect costs and discuss approaches in cost collection by partners | 7.2.1 | 2020-04-30 | 2020-06-30
7.2.3 | Define metrics for the PaN EOSC | - | 2020-04-30 | 2020-11-30
7.2.4 | Collect costs and adjust methodology or scope | 7.2.2 | 2020-06-30 | 2020-09-30
7.2.5 | Complete cost collection and eventually adjust scope | 7.2.4 | 2020-10-01 | 2021-03-01 | M1 | Modified: original 31/12/2020
7.2.6 | Analysis of the cost drivers | 7.2.5 | 2021-03-02 | 2021-04-30 |  | Modified: original 01/01/2021 - 30/04/2021
7.2.7 | First draft of Deliverable 7.2 | 7.2.6 | 2020-12-01 | 2021-06-30 | M2
7.2.8 | Revision of deliverable 7.2 in WP7 | 7.2.7 | 2021-06-01 | 2021-09-30
7.2.9 | Revision of deliverable 7.2 by PMC and submission | 7.2.8 | 2021-10-01 | 2021-11-30
Task 7.3 | Business models for Photon and Neutron EOSC | - | 2019-12-01 | 2022-05-31
7.3.1 | Definition of value proposition | - | 2019-12-01 | 2020-11-30
7.3.2 | Funding and business models feedback | 7.2.4 | 2020-07-01 | 2021-09-30
7.3.3 | Prepare draft business model | 7.3.2 | 2021-10-01 | 2021-12-31 | M3
7.3.4 | Revision of D7.3 in WP7 | 7.3.3 | 2022-01-01 | 2022-04-01
7.3.5 | Revision of deliverable 7.3 by PMC and submission | 7.3.4 | 2022-04-01 | 2022-05-31
Task 7.4 | Sustainability plan for the Photon and Neutron EOSC |  | 2020-06-01 | 2022-11-30
7.4.1 | Identify issues relevant to the sustainability of the PaNOSC | - | 2020-06-01 | 2022-01-01
7.4.2 | Collect information on the EOSC last developments | - | 2020-06-02 | 2022-01-01
7.4.3 | Proposals for the governance of PANOSC outputs | 7.4.1, 7.4.2 | 2021-06-01 | 2022-01-01
7.4.4 | Prepare draft sustainability plan | 7.4.1, 7.4.2, 7.4.3 | 2022-01-01 | 2022-06-30 | M4
7.4.5 | Sustainability plan update and review in WP7 | 7.4.3 | 2022-07-01 | 2022-09-30
7.4.6 | Revision of deliverable 7.4 by PMC and submission | 7.4.4 | 2022-10-01 | 2022-11-30